## Sheet1
Task | Hours | Description
HW_Reqs | 8 | document hw reqs and specs; design & draw UML diagram
HW_Integration | 16 | build preliminary circuit (for initial tests only); calirbate sensors; validate concept of design
HW_Test_Pretest | 16 | test accuracy and limits of full system and/or of preliminary circuit
HW_Build_Full | 32 | build physical support for system (mannequin); tune sensors for final execution environment
SW_uC_1_Reqs | 4 | document reqs&specs for uC subsystem
SW_uC_2_Design_1 | 4 | preliminary design
SW_uC_2_IF | 4 | define interfaces
SW_uC_2_Design_2 | 4 | final design
SW_uC_3_hwcomm | 8 | build hw communication module
SW_uC_3_pcomm | 16 | build PC communication module
SW_PC_1_Reqs | 4 | reqs&specs for PC subsystem
SW_PC_2_Design_1 | 8 | preliminary design
SW_PC_2_Design_2 | 8 | final design
SW_PC_3_IF | 8 | define interfaces
SW_PC_3_GUI | 40 | build GUI application
SW_PC_3_Engine | 16 | build uC communication module and backend
SW_PC_3_Pretest | 8 | run preliminary tests on SW
SYS_hwfinal | 8 | design and run full tests on HW subsystem
SYS_swfinal | 8 | design and run full tests on SW subsystem
SYS_FullTest | 8 | design and run full system tests
SYS_Doc | 16 | finish general documentation
SYS_Validation | 8 | live test
TOTAL HOURS | 252 | 32 workdays